## Slide 1
Design (since Jan, 2018)
Call for Researchers
Panel Survey
Phase I - Replication
Phase II – Research Designs & Deliberation Experiment
Phase III - Expansion
Phase IV – Post-Result Deliberation & Peer Review
OSSC19 Announced
4/5/2018
Pre-analysis Plan
8/22/2018
OSSC19
1/25/2019
Power Analyses
Mar
Mar
Mar
Mar
Mar
Mar
Mar
Mar
Mar
Mar
Mar
Mar
2019
2018

## Slide 2
Design
Call for Researchers
Panel Survey
Replication
Research Designs &
Deliberation Experiment
Expansion
Post Deliberation &
Peer Review
OSSC19 Announced
4/5/2018
1st PAP
8/22/2018
OSSC19
1/25/2019
Power analyses
Jan..
..Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
2019
2018
W1
W2
W3
W4
Original authors
informed
- - - - - - - - - - - - - Design updating - - - - - - - - - - - - -
Final decision
to replicate
Brady & Finnigan (2014)
Phase I
Phase II
Phase III
Phase IV
Figure 1. Crowdsourced Replication Initiative Timeline
2nd PAP
11/24/2018

## Slide 3
Call for Researchers
Survey Wave 1
Replication
Expansion
Post-Results Deliberation
50
55
60
65
70
75
95
Figure 2. CRI Participation Rate
100
90
85
80
Number of Teams
105
Number of
Researchers
215
187
186
163
136a
a ‘Full Participation’ required completion of the Replication and Expansion, not necessarily the Deliberation

## Slide 4
Jan..
Design
Call for Researchers
Panel Survey
Replication
Research Designs &
Deliberation Experiment
Main Analysis
Post Deliberation &
Peer Review
OSSC19 Announced
4/5/2018
1st PAP
8/22/2018
OSSC19
1/25/2019
..Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb..
2019
2018
W2
W3
W4
Design updating
Phase I
Phase II
Phase III
Phase IV
2nd PAP
11/24/2018
Analyzing Results
..Nov
Power analyses
2020
Original authors
informed
Final decision
to replicate
Brady & Finnigan (2014)
W1